## Sheet1
Build Address out of Inventory |  |  |  | updated: | 2021-06-05 |  | printed: | 2021-06-23 | [8 empty] | 7-1-20 to 6-30-21 | 7-1-21 to 6-30-22 | 7-1-22 to 6-30-23 | 7-1-20 to 6-30-21 | 7-1-21 to 6-30-22 | 7-1-22 to 6-30-23 |  |  | Grants
April 1, 2020 to March 31, 2021 |  |  |  | Neighborhood / Township | Development | Type | Sponsers / Partners | Family Info | Family Name | Acquisition Photo SHPO | Permit Applied Date | Permit Received Date | Target House Match Date | Kickoff Mtg Date | Mobilization complete date | start date (super there) | c of o date FY21 | c of o date FY22 | c of o date FY23 | sale date FY21 | sale date FY22 | sale date FY23 | Estimated FMV | Sponsor Partner $ | AHC Rehab | AHC Nwbld | FHLB 2018 | FHLB 2020 | Niag Fuel | LISC NCST | LISC Masten | COD ESD 20 | Grant $ | SONYMA Mortgage $ |  | Notes
1 | Tom | 134 Woodell | R-5 | Cheektowaga | Waden Ave | rhab | Matt Urban | Sold | [6 empty] | done |  | 2020-12-15 |  |  | 2021-02-28 |  |  | 160000 | 160000 | [8 empty] | 0 |  | 160000
2 | Dg/Pt | 148 Laird | R-5 | Riverside | Laird Ave | rcyl | ReStore | Occupied | [6 empty] | done |  | 2020-10-31 |  |  | 2021-03-15 |  |  | 160000 | 0 |  |  |  |  | 5000 |  |  |  | 28000 | 118000 | 151000
3 | Pete | 41 Guliford | Rcyl 4 bdrm ranch | Broadway Filmore | Guliford | rcyl |  | Occupied | [6 empty] | done |  | 2020-10-31 |  |  | 2021-03-15 |  |  | 128000 | 0 | [8 empty] | 0 |  | 0
4 | Doug | 162 Rose | Floyd | Friut Belt | Rose Street | nbld | FBCLT Kaleida | Occupied | [6 empty] | done |  | 2021-04-27 |  |  |  | 2021-10-27 |  | 138000 | 272000 | [8 empty] | 0 |  | 272000
5 | Doug | 166 Rose | Floyd | Friut Belt | Rose Street | nbld | FBCLT M&T | Matched | [6 empty] | done |  | 2021-06-30 |  |  |  | 2021-12-30 |  | 138000 | 232000 | [8 empty] | 0 |  | 232000
6 | Pete | 171 Hastings | R-4 | Kensington Bailey | Kensington | rhab | NCST LISC | Matched | [6 empty] | done |  | 2021-06-30 |  |  |  | 2022-03-31 |  | 90000 |  | rhb2021 |  |  |  |  | yes |  |  | 0 |  | 0
7 | Tom | 20 Andrews | R-3 | Cheektowaga | Pine Hill | rhab | BENLIC | Matched | [6 empty] | done |  | 2021-04-27 |  |  |  | 2022-03-31 |  | 128000 |  | rhb2021 |  |  | yes | no |  |  |  | 58000 |  | 58000
8 | Glenn | 36 Winslow | Wake Mod-3 | Masten Park | Kingsley | nbld | Thrivent Bld 21 | Matched | [5 empty] | 2021-03-09 | 2021-03-17 | 2021-04-02 | 2021-06-30 |  |  |  | 2021-10-31 |  | 140000 | thrivent $ |  | nbd2021 |  | yes |  |  | yes |  | 0 |  | 0
9 | Glenn | 40 Winslow | Wake Mod-5 | Masten Park | Kingsley | nbld |  | Matched | [5 empty] | 2021-03-09 | 2021-03-17 | 2021-04-02 | 2021-06-30 |  |  |  | 2021-10-31 |  | 150000 |  |  | nbd2021 |  | yes |  |  | yes |  | 0 |  | 0
10 | Glenn | 1363 Michigan | Wake Mod-4 | Masten Park | Laurel/Michigan | nbld |  | Matched | [5 empty] | 2021-03-09 | 2021-03-17 | 2021-04-05 | 2021-06-30 |  |  |  | 2021-11-30 |  | 150000 |  |  | nbd2021 |  | yes |  |  | yes |  | 0 |  | 0
11 | Glenn | 136 West Ferry | Wake Mod-3 | Upper West Side | West Ferry | nbld | Thrivent Bld 20 | Matched | [5 empty] | 2021-03-09 | 2021-04-16 | 2021-04-01 | 2021-06-30 |  |  |  | m |  | 160000 | thrivent $ | [5 empty] | yes |  |  | 0 |  | 0
[14 empty] | -45 |  |  | 7-1-20 to 6-30-21 | 7-1-21 to 6-30-22 | 7-1-22 to 6-30-23 | 7-1-20 to 6-30-21 | 7-1-21 to 6-30-22 | 7-1-22 to 6-30-23
April 1, 2021 to March 31, 2022 |  |  |  | Neighborhood / Township | Development | Type | Sponsers / Partners | Family Info | Family Name | Acquisition Photo SHPO | Permit Applied Date | Permit Received Date | Target House Match Date | Kickoff Mtg Date | Mobilization complete date | start date (super there) | c of o date FY21 | c of o date FY22 | c of o date FY23 | sale date FY21 | sale date FY22 | sale date FY23 | Estimated FMV |  | AHC Rehab | AHC Nwbld | FHLB 2018 | FHLB 2020 | Niag Fuel | LISC NCST | LISC Masten | COD ESD 20 | Grant $ |  |  | Notes
1 | Doug | 33 Brunswick | ACES 3 bdrm Nwbld | Hamlin Park | Brunswick | nbld | Ham Prk Tax Assoc. | Mutoni Flavia | [6 empty] | 2021-05-01 | 2021-04-20 |  | 2021-12-16 |  |  | 2022-03-01 |  | 155000 | 15000 |  | substitute
2 | Doug | 59 Verplanck | Floyd 4bdrm | Masten Park | Masten | nbld | [7 empty] | 2021-03-17 | 2021-05-01 | 2021-05-03 |  | 2022-01-22 |  |  | 2022-02-15 |  | 145000 |  |  | nbd2021 |  |  |  |  | applied
3 | Doug | 65 Verplanck | Floyd 4bdrm | Masten Park | Masten | nbld |  | Mohammed Ababulgu | [5 empty] | 2021-03-17 | 2021-05-01 | 2021-06-07 |  | 2022-02-26 |  |  | 2022-03-22 |  | 145000 |  |  | nbd2021
4 | Doug | 69 Verplanck | 4 bdrm Ranch accessable | Masten Park | Masten | nbld |  | Bandora Vitali | [5 empty] | 2021-06-15 | 2021-07-30 | 2021-07-12 |  | 2022-04-02 |  |  | 2022-04-26 |  | 145000 |  |  | nbd2021
5 | Pete | 19 Phyllis | R-4 1.5 Bath | Kensington Bailey | Kensington | rhab | NCST LISC | [6 empty] | 2021-03-09 | 2021-04-17 | 2021-04-27 |  | 2021-12-23 |  |  | 2022-03-31 |  | 90000 |  | rhb2021 |  |  | yes |  | yes | [5 empty] | NCST Drop Dead C of O by 11-30-21
6 | Pete | 204 Woodlawn | R-5 | Masten Park | Masten | rhab | Beer Bld 2019 | Matched | [5 empty] | 2021-03-09 | 2021-04-16 | 2021-04-20 |  | 2022-01-29 |  |  | 2022-03-31 |  | 120000 |  | rhb2021 |  | yes |  |  |  | yes
7 | Pete | 117 Center St | Floyd 4bdrm | Lackawanna | First Ward | nbld | CHDO LHDC | Kimberly Hale | need site control |  |  |  |  | 2021-06-07 | 2021-07-22 | 2021-08-02 |  | 2022-03-05 |  |  | 2022-03-29 |  | 130000
8 | Pete | 114 or 116 Center St | 4 bdr Ranch | Lackawanna | First Ward | nbld | CHDO LHDC |  | need site control |  |  |  |  | 2021-07-12 | 2021-08-26 | 2021-09-06 |  | 2022-04-09 |  |  | 2022-05-03 |  | 140000
9 | Rich | 142 Wende | Ranch O BOCES 3bdrm | Genesee Moselle | Bailey Green | nbld | [7 empty] | 2021-05-05 | 2021-06-19 | 2021-07-06 |  | 2021-11-01 |  |  | 2022-02-22 |  | 125000 |  |  | nbd2021 | [9 empty] | austin "working on permits (6-21-21)"
10 | Rich | 37 Haven | R-3 | Schiller Park | Haven | rhab | [14 empty] | 2022-04-30 |  | 80000 |  | rhb2021 |  |  | yes | yes |  |  | yes
11 | Greg | 87 O'Connor | Recycle 3 | South Park | O'Connor
12 | Greg | 29 Minton | R-5 | Seneca Babcock | Minton | rhab |  | Abuk Mawen | [19 empty] | yes |  |  |  | yes
13 | Mike | 312 Busti | Wake Mod-5 | West Side | Lakeview | nbld |  | Matched | [14 empty] | 165000 |  |  | nbld2021 |  | yes
14 | Mike | 423 Busti | Wake Mod-4 | West Side | Lakeview | nbld |  | Matched | [14 empty] | 155000 |  |  | nbd2021 |  | yes
15 | Mike | 503 Busti | Wake Mod 5 | West Side | Lakeview | nbld |  | Matched | [14 empty] | 165000 |  |  | nbd2021 |  | yes
xx | Glenn | 63 Zenner | Ranch P BOCES 3bdrm | Genesee Moselle | Bailey Green | nri |  | Peacemakers
xx | Glenn | 79 Kilhoffer | Custom Fact Bld Mod | Genesee Moselle | Bailey Green | nri |  | Peacemakers
xx | Glenn | 162 Zenner (Youth Bld) | R-3 | Genesee Moselle | Bailey Green | rhab | [16 empty] | 80000 |  | rhb2021? |  | yes
xx | Glenn | Potter BOCES 20-22 | School Bld Mod 3bdrm | xxxx TBD xxxx | xxxx TBD xxxx | nbld
xx | Glenn | Orleans BOCES 21-22 | School Bld Mod 3bdrm | xxxx TBD xxxx | xxxx TBD xxxx | nbld
Addresses lock 12-31-2021 |  | April 1, 2022 to March 31, 2023 |  | Neighborhood / Township | Development | Type | Sponsers / Partners | Family Info | Family Name | Acquisition Photo SHPO | Permit Applied Date | Permit Received Date | Target House Match Date | Kickoff Mtg Date | Mobilization complete date | start date (super there) | c of o date FY21 | c of o date FY22 | c of o date FY23 | sale date FY21 | sale date FY22 | sale date FY23 | Estimated FMV |  | AHC Rehab | AHC Nwbld | FHLB 2018 | FHLB 2020 | Niag Fuel | LISC NCST | LISC Masten | COD ESD 20 |  |  |  | Sponsor / Funder
1 | new 1 | 83 Pinehurst | Ranch Site bld 3 or 4 | Cheektowaga | U-Crest | nbld |  | Confirm Match | [7 empty] | 2022-04-21 |  |  | 2022-12-17 |  |  | 2023-03-31 | 125000 |  |  | nbd2021
2 | new 1 | 95 Pinehurst | Ranch Site bld 3 or 4 | Cheektowaga | U-Crest | nbld | [9 empty] | 2022-05-04 |  |  | 2023-01-23 |  |  | 2023-03-31 | 125000 |  |  | nbd2021
3 | new 1 | [14 empty] | 2022-06-08 |  |  | 2023-02-27 |  |  | 2023-03-31
4 | new 1 | [14 empty] | 2022-07-13 |  |  | 2023-04-03 |  |  | 2023-04-30
5 | Pete | 52 Olcott | R-3? | Cheektowaga | Pine Hill | rhab |  | need to acquire | [7 empty] | 2022-04-28 |  |  | 2022-12-24 |  |  | 2023-03-31 | 125000 |  | rhb2022
6 | Pete | 118 Carol | 3-4-5 Newbuild | Cheektowaga | Pine Hill | nbld | [9 empty] | 2022-07-07 |  |  | 2022-11-02 |  |  | 2023-02-28 | 140000 |  |  | nbd2021
7 | Pete | 51 East End | 3-4-5 Newbuild | Cheektowaga | Pine Hill | nbld | [9 empty] | 2022-08-03 |  |  | 2023-03-06 |  |  | 2023-03-31 | 130000 |  |  | nbd2021
8 | Pete | 38 Barbara | 3-4-5 Newbuild | Cheektowaga | Pine Hill | nbld | [9 empty] | 2022-09-07 |  |  | 2023-04-10 |  |  | 2023-04-30 | 140000 |  |  | nbd2021
9 | Doug | 188 Glenwood | 3-4-5 Newbuild | Masten Park | Masten | nbld | [9 empty] | 2022-07-07 |  |  | 2022-11-02 |  |  | 2023-01-31 | 145000 |  |  | nbd2021
10 | Doug | Masten Park | 3-4-5 Newbuild | Masten Park |  | nbld |  | need to acquire | [7 empty] | 2022-05-04 |  |  | 2023-01-23 |  |  |  | 145000
11 | Doug | Masten Park | 3-4-5 Newbuild | Masten Park |  | nbld |  | need to acquire | [7 empty] | 2022-06-08 |  |  | 2023-02-27 |  |  |  | 145000
12 | Doug | Masten Park | 3-4-5 Newbuild | Masten Park |  | nbld |  | need to acquire | [7 empty] | 2022-07-13 |  |  | 2023-04-03 |  |  |  | 145000
13 | new 2 | [14 empty] | 2022-04-28 |  |  | 2022-10-25 |  |  | 2023-03-31 | 90000 |  | rhb2022
14 | new 2 | 82 Florence | Lot in West Seneca | West Seneca | Corner Center | nbld | Veterans One Stop | [8 empty] | 2022-07-07 |  |  | 2023-01-03
15 | new 2 | 1574 E Delevan | R-5 | Cheektowaga | Pine Hill | rhab |  | need to acquire | [7 empty] | 2022-10-19 |  |  | 2023-04-17 |  |  | 2023-04-30 | 125000 |  | rhb2022
16 | new 2 | 1576 E Delevan | R-5 | Cheektowaga | Pine Hill | rhab |  | need to acquire | [7 empty] | 2022-10-20 |  |  | 2023-05-18 |  |  | 2023-05-31 | 125000 |  | rhb2022
17 | Glenn | 121 Montclair | 3-4-5 Newbuild wakefiled | Fillmore Leroy | Leroy | nbld |  | need to acquire | [14 empty] | 155000
18 | Glenn | 125 Montclair | 3-4-5 Newbuild wakefiled | Fillmore Leroy | Leroy | nbld |  | need to acquire | [14 empty] | 155000
19 | Glenn | 568 Hopkins | 3-4-5 Newbuild wakefiled | Hopkins Tift | Triangle | nbld
20 | Glenn | 580 Hopkins | 3-4-5 Newbuild wakefiled | Hopkins Tift | Triangle | nbld | [16 empty] | 155000
21 | Glenn | (144)148 Wende | Ranch P BOCES 21-22 | Genesee Moselle | Bailey Green | nbld |  | need to acquire | [6 empty] | pull 6-2022 | [7 empty] | 125000 |  |  | nbd2021
22 | Glenn | 149 Wende | Ranch O BOCES 21-22 | Genesee Moselle | Bailey Green | nbld | [8 empty] | pull 6-2022 | [7 empty] | 125000 |  |  | nbld2021
Still in inventory |  |  |  | Neighborhood / Township | Development | Type |  |  |  | Acquisition Photo SHPO | [14 empty] | AHC Rehab | AHC Nwbld | FHLB 2018 | FHLB 2020 | Niag Fuel | LISC NCST | LISC Masten | COD ESD 20
|  | 179 Westmeinster | R-? | Kensington Bailey | Kensington | rhab |  | need to acquire
|  | 147 Zenner | Rehab Bailey Green | Genesee Moselle | Bailey Green | rhab | [25 empty] | yes
|  | 152 Sprenger | Rehab | Schiller Park |  | rhab | [20 empty] | yes
|  | 171 Keystone | Lot | Schiller Park |  | nbld | [19 empty] | nbd2021
|  | 85 Haven | R-4/5 | Schiller Park |  | rhab | [25 empty] | yes
|  | 33 Zenner | Lot Bailey Green | Genesee Moselle | Bailey Green | nbld | [19 empty] | nbd2021
|  | 114 Wende | Lot Bailey Green | Genesee Moselle | Bailey Green | nbld | [19 empty] | nbd2021
Likely to come to inventory
|  | 127 Kay St | Rehab | Kensington Bailey | Kensington | rhab
|  | 114 or 116 Center St | Floyd or Ranch Site bld | Lackawanna | First Ward | nbld
|  | 235 Esser | Double Lot Riverside 3-4-5 | Riverside | Esser-Henrietta | nbld
|  | 73 Barnard | Rehab in Kaisertown | Kaisertown | Barnard | rhab | Has asbestos problem
|  | 168 Howard | Lot in Broadway Fillmore | Emslie | Corner Krettner | nbld
C:\Users\tojumu\AppData\Local\Microsoft\Windows\INetCache\Content.Outlook\3N2R7KO5\[2020-2021-2022 Build Addresses Board Presentation 6-22-21.xlsx]Floyd
Formulas:
sale date FY22 = [c of o date FY21]+183
sale date FY22 = [sale date FY22, row above]+35
Kickoff Mtg Date = [Mobilization complete date]-45
c of o date FY22 = [start date (super there)]+240
c of o date FY22 = [c of o date FY22, row below]-35
start date (super there) = [start date (super there), row above]+35
c of o date FY23 = [start date (super there)]+180
Note on P2: Rick Folger: Mobilzation Complete is different for each type of buld i.e. nwbld rehab, recycle, fact blt mod, school blt mod
Note on Y7: Rick Folger: 192 K from FBCLT and 80k from Kalida
Note on Y8: Rick Folger: 192 K from FBCLT and 40k from M&T
Note on O11: Keelan Erhard: Pink shading donates scheduled.
Note on Q11: Rick Folger: Set Date for Factory Built Modulars
Note on Q12: Rick Folger: Set Date for Factory Built Modulars
Note on Q13: Rick Folger: Set Date for Factory Built Modulars
Note on I14: Keelan Erhard: < 60% AMI
Note on Q14: Rick Folger: Set Date for Factory Built Modulars
Note on P16: Rick Folger: Mobilzation Complete is different for each type of buld i.e. nwbld rehab, recycle, fact blt mod, school blt mod
Note on S18: Rick Folger: 6 months to complete? 26 weeks at 3 site super days per week equals 78 super days
Note on Y18: Rick Folger: 15k Hamlin Park Tax Payer Association
Note on D26: Rick Folger: Orleans BOCES 19-21
Note on Q30: Rick Folger: Set Date for Factory Built Modulars
Note on Q31: Rick Folger: Set Date for Factory Built Modulars
Note on Q32: Rick Folger: Set Date for Factory Built Modulars
Note on D33: Rick Folger: Potter Rd BOCES 19-20. Currently Stored.
Note on Q33: Rick Folger: Set Date for School Built Modular
Note on P38: Rick Folger: Mobilzation Complete is different for each type of buld i.e. nwbld rehab, recycle, fact blt mod, school blt mod
Note on D60: Rick Folger: Potter Rd BOCES 20-22
Note on I60: Rick Folger: need to acquire 148 Wende
Note on D61: Rick Folger: Orleans BOCES 21-22

## Floyd
| Time Period A |  | Time Period B |  | Time Period C |  |  | Time Period D |  |  | Time Period E | [9 empty] | Time Period F |  | Time Period G | [5 empty] | Time Period H |  |  |  |  | Time Period I
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
week ending date
 | time axis 2021-04-25 to 2022-04-17
Newbld 1 | 2021-04-25: First Floor Framing; 2021-05-09: Truss, Roof, Facia, Soffit, Rakes; 2021-05-23: Rgh Porch, Window, Door, Siding, Porch Finsh 2nd flr interior framing; 2021-06-13: Rgh Elec, Plumb, HVAC, Driveway, Curb, Sidewalk, Gutters; 2021-07-04: Lawn; 2021-09-12: Insullation Drywall Hanging Shed; 2021-09-26: Drywall Finishing; 2021-11-07: Paint, Our Flooring Iterior Trim & Doors Cabinets Finsh Plumb Elect HVAC Accessories; 2021-12-12: Carpet
Newbld 2 | 2021-05-09: First Floor Framing; 2021-05-23: Truss, Roof, Facia, Soffit, Rakes; 2021-06-13: Rgh Porch, Window, Door, Siding, Porch Finsh 2nd flr interior framing; 2021-07-04: Rgh Elec, Plumb, HVAC, Driveway, Curb, Sidewalk, Gutters; 2021-07-25: Lawn; 2021-09-26: Insullation Drywall Hanging Shed; 2021-10-10: Drywall Finishing; 2021-12-12: Paint, Our Flooring Iterior Trim & Doors Cabinets Finsh Plumb Elect HVAC Accessories; 2022-01-16: Carpet
Newbld 3 | 2021-07-04: First Floor Framing; 2021-07-18: Truss, Roof, Facia, Soffit, Gutter; 2021-08-01: Rgh Porch, Window, Door, Siding, Porch Finsh 2nd flr interior framing; 2021-08-22: Rgh Elec, Plumb, HVAC, Driveway, Curb, Sidewalk, Gutters; 2021-09-12: Lawn; 2021-10-10: Insullation Drywall Hanging Shed; 2021-10-24: Drywall Finishing; 2022-01-16: Paint, Our Flooring Iterior Trim & Doors Cabinets Finsh Plumb Elect HVAC Accessories; 2022-02-20: Carpet
Newbld 4 | 2021-07-18: First Floor Framing; 2021-08-01: Truss, Roof, Facia, Soffit, Gutter; 2021-08-22: Rgh Porch, Window, Door, Siding, Porch Finsh 2nd flr interior framing; 2021-09-12: Rgh Elec, Plumb, HVAC, Driveway, Curb, Sidewalk, Gutters; 2021-10-03: Lawn; 2021-10-24: Insullation Drywall Hanging Shed; 2021-11-07: Drywall Finishing; 2022-02-20: Paint, Our Flooring Iterior Trim & Doors Cabinets Finsh Plumb Elect HVAC Accessories; 2022-03-27: Carpet
Women Build Week
[23 empty] | Possible Leaders Build Week | Possible Leaders Build Week
| week ending date |  | week ending date
 | time axis 2021-04-25 to 2022-04-17
162 Rose | bar: 2021-05-16
166 Rose | 2021-05-23: Or have him work at 204 Woodlawn?
33 Brunswick | 2021-06-06: ? HTO Rim Sill Flr Joist to Deck; 2021-06-13: ? HTO Rim Sill Flr Joist to Deck; 2021-06-20: First Floor Framing; 2021-07-04: 2nd Floor Framing; 2021-07-18: Truss, Roof, Facia, Soffit, Gutter; 2021-08-01: Rgh Porch, Window, Door, Siding, Porch Finsh Shed; 2021-08-22: Rgh Elec Plumb HVAC Driveway Curb Sidewalk; 2021-10-10: Insullation Drywall Hanging; 2021-10-24: Drywall Finishing; 2022-01-16: Paint, Our Flooring Iterior Trim & Doors Cabinets Finsh Plumb Elect HVAc Accessories; 2022-02-20: Carpet
59 Verplanck | 2021-05-09: 1st Floor Deck and Walls; 2021-05-16: HTO First Floor Framing and Rough Porch; 2021-05-23: Truss and Roof; 2021-05-30: 2nd Floor Framing; 2021-06-06: Window, Door, Siding, Porch Finsh Shed; 2021-06-13: Window, Door, Siding, Porch Finsh Shed; 2021-06-20: Rgh Elec Plumb HVAC Driveway Curb Sidewalk; 2021-07-18: First Floor Framing; 2021-08-01: Truss, Roof, Facia, Soffit, Gutter; 2021-08-22: Rgh Porch, Window, Door, Siding, Porch Finsh Shed; 2021-09-12: Rgh Elec Plumb HVAC Driveway Curb Sidewalk; 2021-10-24: Insullation Drywall Hanging; 2021-11-07: Drywall Finishing; 2022-02-20: Paint, Our Flooring Iterior Trim & Doors Cabinets Finsh Plumb Elect HVAc Accessories; 2022-03-27: Carpet
65 Verplanck | 2021-05-09: 1st Floor Deck and Walls; 2021-05-16: HTO First Floor Framing and Rough Porch; 2021-05-23: Truss and Roof; 2021-05-30: 2nd Floor Framing; 2021-06-06: Window, Door, Siding, Porch Finsh Shed; 2021-06-13: Window, Door, Siding, Porch Finsh Shed; 2021-06-20: Rgh Elec Plumb HVAC Driveway Curb Sidewalk; 2021-07-18: Truss, Roof, Facia, Soffit, Gutter; 2021-08-01: Rgh Porch, Window, Door, Siding, Porch Finsh Shed; 2021-08-22: Rgh Elec Plumb HVAC Driveway Curb Sidewalk; 2021-10-10: Insullation Drywall Hanging; 2021-10-24: Drywall Finishing; 2022-01-16: Paint, Our Flooring Iterior Trim & Doors Cabinets Finsh Plumb Elect HVAc Accessories; 2022-02-20: Carpet
69 Verplanck | 2021-07-18: First Floor Framing; 2021-08-01: Truss, Roof, Facia, Soffit, Gutter; 2021-08-22: Rgh Porch, Window, Door, Siding, Porch Finsh Shed; 2021-09-12: Rgh Elec Plumb HVAC Driveway Curb Sidewalk; 2021-10-24: Insullation Drywall Hanging; 2021-11-07: Drywall Finishing; 2022-02-20: Paint, Our Flooring Iterior Trim & Doors Cabinets Finsh Plumb Elect HVAc Accessories; 2022-03-27: Carpet

## C of O deadlines
C of O Deadlines |  |  |  |  | Grants
April 1, 2020 to March 31, 2021 |  |  |  | HFHI Reporting | AHC Rehab | AHC Nwbld | FHLB 2018 | FHLB 2020 | Niag Fuel | LISC NCST | LISC Masten | COD ESD 20
1 | Tom | 134 Woodell | R-5
2 | Dg/Pt | 148 Laird | R-5 | [5 empty] | 5000
3 | Pete | 41 Guliford | Rcyl 4 bdrm ranch
4 | Doug | 162 Rose | Floyd
5 | Doug | 166 Rose | Floyd
6 | Pete | 171 Hastings | R-4 |  | rhb2021 |  |  |  |  | 2021-10-31
7 | Tom | 20 Andrews | R-3 |  | rhb2021 |  |  | yes | no
8 | Glenn | 36 Winslow | Wake Mod-3 |  |  | nbd2021 |  | yes |  |  | 2021-12-31
9 | Glenn | 40 Winslow | Wake Mod-5 |  |  | nbd2021 |  | yes |  |  | 2021-12-31
10 | Glenn | 1363 Michigan | Wake Mod-4 |  |  | nbd2021 |  | yes |  |  | 2021-12-31
11 | Glenn | 136 West Ferry | Wake Mod-3 | [6 empty] | 2021-06-30
April 1, 2021 to March 31, 2022 |  |  |  |  | AHC Rehab | AHC Nwbld | FHLB 2018 | FHLB 2020 | Niag Fuel | LISC NCST | LISC Masten | COD ESD 20
1 | Doug | 33 Brunswick | ACES 3 bdrm Nwbld |  |  | substitute
2 | Doug | 59 Verplanck | Floyd 4bdrm |  |  | nbd2021
3 | Doug | 65 Verplanck | Floyd 4bdrm |  |  | nbd2021
4 | Doug | 69 Verplanck | 4 bdrm Ranch accessable |  |  | nbd2021
5 | Pete | 19 Phyllis | R-4 1.5 Bath |  | rhb2021 |  |  | yes |  | 2021-11-30 |  |  | 70% AMI Lisc
6 | Pete | 204 Woodlawn | R-5 |  | rhb2021 |  | yes |  |  |  | 2021-12-31
7 | Pete | 117 Center St | Floyd 4bdrm
8 | Pete | 114 or 116 Center St | 4 bdr Ranch
9 | x | 142 Wende | Ranch O BOCES 3bdrm |  |  | nbd2021
10 | x | 37 Haven | R-3 |  | rhb2021 |  |  | yes | yes |  |  | yes
11 | x | 29 Minton | R5? |  |  |  |  | yes |  |  |  | yes
12 | Glenn | 312 Busti | Wake Mod-5 |  |  | nbld2021 |  | yes
13 | Glenn | 423 Busti | Wake Mod-4 |  |  | nbd2021 |  | yes
14 | Glenn | 503 Busti | Wake Mod 5 |  |  | nbd2021 |  | yes
15 | Glenn | 114 Wende | Ranch P BOCES 3bdrm |  |  | nbd2021
xx | Glenn | 63 Zenner | Ranch P BOCES 3bdrm
xx | Glenn | 79 Kilhoffer | Custom Fact Bld Mod
16 | Glenn | 162 Zenner (Youth Bld) | R-3 |  | rhb2021? |  | yes
xx | Glenn | Potter BOCES 20-22 | School Bld Mod 3bdrm
xx | Glenn | Orleans BOCES 21-22 | School Bld Mod 3bdrm
Addresses lock 12-31-2021 |  | April 1, 2022 to March 31, 2023 |  |  | AHC Rehab | AHC Nwbld | FHLB 2018 | FHLB 2020 | Niag Fuel | LISC NCST | LISC Masten | COD ESD 20
1 | new 1 | 83 Pinehurst | Ranch Site bld 3 or 4 |  |  | nbd2021
2 | new 1 | 95 Pinehurst | Ranch Site bld 3 or 4 |  |  | nbd2021
3 | new 1 | 235 Esser | Double Lot Riverside 3-4-5
4 | new 1 | 23x Esser | Double Lot Riverside 3-4-5
5 | Pete | 52 Olcott | R-3? |  | rhb2022
6 | Pete | 118 Carol | 3-4-5 Newbuild |  |  | nbd2021
7 | Pete | 51 East End | 3-4-5 Newbuild |  |  | nbd2021
8 | Pete | 38 Barbara | 3-4-5 Newbuild |  |  | nbd2021
9 | Doug | 188 Glenwood | 3-4-5 Newbuild |  |  | nbd2021
10 | Doug | Masten Park | 3-4-5 Newbuild
11 | Doug | Masten Park | 3-4-5 Newbuild
12 | Doug | Masten Park | 3-4-5 Newbuild
13 | new 2 | 29 Minton | R5? |  | rhb2022
14 | new 2 | 82 Florence | Lot in West Seneca
15 | new 2 | 1574 E Delevan | R-5 |  | rhb2022
16 | new 2 | 1576 E Delevan | R-5 |  | rhb2022
17 | Glenn | 121 Montclair | 3-4-5 Newbuild wakefiled
18 | Glenn | 125 Montclair | 3-4-5 Newbuild wakefiled
19 | Glenn | 568 Hopkins | 3-4-5 Newbuild wakefiled
20 | Glenn | 580 Hopkins | 3-4-5 Newbuild wakefiled
21 | Glenn | (144)148 Wende | Ranch P BOCES 21-22 |  |  | nbd2021
22 | Glenn | 149 Wende | Ranch O BOCES 21-22 |  |  | nbld2021
Still in inventory |  |  |  |  | AHC Rehab | AHC Nwbld | FHLB 2018 | FHLB 2020 | Niag Fuel | LISC NCST | LISC Masten | COD ESD 20
|  | 179 Westmeinster | R-? |  |  |  |  | yes ?
|  | 147 Zenner | Rehab Bailey Green | [8 empty] | yes
|  | 152 Sprenger | Rehab |  |  |  | yes
|  | 171 Keystone | Lot |  |  | nbd2021
|  | 85 Haven | R-4/5 | [8 empty] | yes
|  | 33 Zenner | Lot Bailey Green |  |  | nbd2021
Likely to come to inventory
|  | 114 or 116 Center St | Floyd or Ranch Site bld
|  | 73 Barnard | Rehab in Kaisertown
|  | 168 Howard | Lot in Broadway Fillmore
Note on D27: Rick Folger: Orleans BOCES 19-21
Note on D33: Rick Folger: Potter Rd BOCES 20-21. May require lots of finish work due to covid
Note on D34: Rick Folger: Potter Rd BOCES 19-20. Currently Stored.
Note on D61: Rick Folger: Potter Rd BOCES 20-22
Note on D62: Rick Folger: Orleans BOCES 21-22

## Foundations
Foundation Schedule for 2021-22 Build Sesason |  |  |  | updated: | 2021-03-24
(April 1, 2021 to March 31, 2022) |  |  |  | printed: | 2021-06-23
| Address | Type | Completion by date* | Status / Concerns | Notes
1 | 36-38 Winslow | Wake Mod-3 | 2021-04-15
2 | 40 Winslow | Wake Mod-5 | 2021-04-15
3 | 1363 Michigan | Wake Mod-4 | 2021-04-22
4 | 136 West Ferry | Wake Mod-3 | 2021-04-22
5 | 59 Verplanck | Floyd | 2021-05-01 | Applied for permit | Dig in 2 weeks as of 3-24-21
6 | 65 Verplanck | Floyd | 2021-05-01 | Applied for permit | Dig in 2 weeks as of 3-24-21
7 | 63 Zenner | Ranch P BOCES 19-20 | 2021-05-31 | Applied for permit Request for revision for plumbing and sewer | Dig in 2 weeks as of 3-24-21
8 | 33 Brunswick | ACES 3 3bdrm | 2021-05-31 | Site Control by April 15th 2021 | Starts sooner if permiting is done
9 | 142 Wende | Ranch O BOCES 19-21 | 2021-06-15 | Hard deadline communicated to Sutton 6-1-21
10 | 114 Wende | Ranch P BOCES 20-21 | 2021-06-15 | Hard deadline communicated to Sutton 6-1-21
11 | 117 Center St | TBD Ranch or floyd | 2021-06-15 | Floyd w Sutton. Next to planning board March 31st | Site Control by April 15th 2021
12 | 114 or 116 Center St | TBD Ranch or floyd | 2021-07-31 | TBD Model & Site Control by April 30th 2021 | TOB working on which address
13 | 69 Verplanck | TBD Ranch or floyd | tbd | TBD Model by April 30th 2021
14 | 79 Kilhoffer | Custom Fact Bld Mod | tbd | TBD Model by May 15th 2021
15 | 312 Busti | Wake Mod-5 | 2021-08-15 |  | Factory build mods
16 | 423 Busti | Wake Mod-4 | 2021-08-15 |  | Factory build mods
17 | 503 Busti | Wake Mod-3-4-5 | 2021-08-15 | TBD Model by June15th 2021 | Factory build mods
*Defining Foundation is complete:
For Factory Modulars: Poured, Forms removed, Waterproofed, Braced (if needed),Backfilled, Sewer & Water from street, Floor poured, Sill plate
For School Blt: Poured, Forms removed, Waterproofed,Steel installed, Braced (if needed),Backfilled, Sewer & Water from street, Floor poured, Sill plate
For Traditional Site Blds: Poured, Forms removed, Waterproofed, Steel installed, Deck installed,Backfilled, Sewer & Water from street, Floor Poured
Note on C11: Rick Folger: Potter Rd BOCES 19-20. Currently Stored.
Note on C13: Rick Folger: BOCES BOCES Orleans pulled after 6-21. Not sure how complete this home will be
Note on C14: Rick Folger: BOCES Potter Road pulled after 6-21. Not sure how complete this home will be

## sales fy22
[6 empty] | 7-1-20 to 6-30-21 | 7-1-21 to 6-30-22 | 7-1-22 to 6-30-23 | 7-1-20 to 6-30-21 | 7-1-21 to 6-30-22 | 7-1-22 to 6-30-23
[6 empty] | c of o date FY21 | c of o date FY22 | c of o date FY23 | sale date FY21 | sale date FY22 | sale date FY23
|  |  |  | C of O date | Move in date
| 1 | 134 Woodell | R-5 |  |  | 2020-12-15 |  |  | 2021-02-28
| 2 | 148 Laird | R-5 |  |  | 2020-10-31 |  |  | 2021-03-31
| 3 | 41 Guliford | Rcyl 4 bdrm ranch |  |  | 2020-10-31 |  |  | 2021-04-15
Doug | 4 | 162 Rose | Floyd | 2021-04-15 | 2021-05-01 | 2021-04-15 |  |  |  | 2021-07-15
Doug | 5 | 166 Rose | Floyd | 2021-05-01 | 2021-06-01 | 2021-05-01 |  |  |  | 2021-07-31
Pete | 6 | 171 Hastings | R-4 | 2021-05-15 | 2021-06-01 | 2021-05-15 |  |  |  | 2022-03-31
| 7 | 20 Andrews | R-3 | 2021-05-01 | 2021-06-01 | 2021-05-01 |  |  |  | 2022-03-31
| 8 | 36 Winslow | Wake Mod-3 | 2021-06-30 | 2021-08-01 | 2021-06-30 |  |  |  | 2021-10-31
| 9 | 40 Winslow | Wake Mod-5 | 2021-06-30 | 2021-08-01 | 2021-06-30 |  |  |  | 2021-10-31
| 10 | 1363 Michigan | Wake Mod-4 | 2021-06-30 | 2021-08-01 | 2021-06-30 |  |  |  | 2021-11-30
| 11 | 136 West Ferry | Wake Mod-3 | 2021-05-31 |  | 2021-05-31 |  |  |  | 2021-11-30
Doug 1 | 1 | 33 Brunswick | ACES 3 bdrm Nwbld |  |  | 2021-12-18 |  |  |  | 2022-02-28
Doug 2 | 2 | 59 Verplanck | Floyd |  |  | 2022-01-22 |  |  |  | 2022-03-31
Doug 3 | 3 | 65 Verplanck | Floyd |  |  | 2022-02-26 |  |  |  | 2022-04-15
Doug 4 | 4 | 69 Verplanck | 4 bdrm Ranch accessable |  |  | 2022-04-02 |  |  |  | 2022-04-30
Pete 1 | 5 | 19 Phyllis | R-4 1.5 Bath |  |  | 2021-11-18 |  |  |  | 2022-04-15
Pete 2 | 6 | 204 Woodlawn | R-5 |  |  | 2022-01-29 |  |  |  | 2022-04-30
Pete 3 | 7 | 117 Center St | Floyd bld |  |  | 2022-03-05 |  |  |  | 2022-03-31
Pete 4 | 8 | 114 or 116 Center St | Floyd or Ranch Site bld |  |  | 2022-04-09 |  |  |  | 2022-04-15
HTO | 9 | 142 Wende | Ranch O BOCES 19-21 | [6 empty] | 2022-05-15
New | 10 | 37 Haven | R-3 | [6 empty] | 2022-05-15
Glenn | 11 | 312 Busti | Wake Mod-5 | [6 empty] | 2022-01-15
Glenn | 12 | 423 Busti | Wake Mod-4 | [6 empty] | 2022-01-31
Glenn | 13 | 503 Busti | Wake Mod 5 | [6 empty] | 2022-02-15
HTO | 14 | 114 Wende | School Bld Mod 3bdrm | [6 empty] | 2022-05-15
Glenn | x | 63 Zenner | Ranch P BOCES 19-20 | [6 empty] | 2021-07-31
Glenn | x | 79 Kilhoffer | Custom Fact Bld Mod | [6 empty] | 2021-10-31
HTO | 15 | 162 Zenner (Youth Bld) | R-3 | [6 empty] | 2022-06-15
Grants (post closing)
[16 empty] | AHC Rehab | AHC Nwbld | FHLB 2018 | FHLB 2020 | Niag Fuel | LISC NCST | LISC Masten | COB ESD 20
|  | 25 Sales: 4 Partner, 2 Partner NRI, 12 NWB HFHB held, 7 SONYMA |  |  |  | Total CIP | FMV | Sold for | Partner Interest Subsidy | Net Sale | SONYMA Interest Subsidy | Closing Cost Funded | NWB- HFHB Mortgage | SONYMA Cash at Table | Partner Cash at Table
| 1 | 162 Rose | Floyd | 2021-07-15 | Partner | 175000 | 150000 | 192000 | 36000 | 156000 |  |  | 0 |  | 156000 |  |  |  |  | 5100
| 2 | 166 Rose | Floyd | 2021-08-15 | Partner | 175000 | 150000 | 192000 | 36000 | 156000 |  |  | 0 |  | 156000 |  |  |  |  | 5100
| 3 | 63 Zenner | Ranch P BOCES 19-20 | 2021-08-30 | Partner NRI | 100000 | x | 80000 |  | 80000 |  |  | 0
| 4 | 36-38 Winslow | Wake Mod-3 | 2021-10-31 | SONYMA | 175000 | 140000 | 140000 |  | 140000 | 33600 | 8000 | 0 | 98400 |  |  | 35000 |  | 30000 | 5100 |  | 30000
| 5 | 40 Winslow | Wake Mod-5 | 2021-10-31 | SONYMA | 185000 | 150000 | 150000 |  | 150000 | 36000 | 8000 | 0 | 106000 |  |  | 35000 |  | 30000 | 5100 |  | 30000
| 6 | 79 Kilhoffer | Custom Fact Bld Mod | 2021-10-31 | Partner NRI | 110000 | x | 90000 |  | 90000 |  |  | 0
| 7 | 1363 Michigan | Wake Mod-4 | 2021-11-30 | NWB-HFHB | 180000 | 150000 | 150000 |  | 150000 |  | 8000 | 158000 |  |  |  | 35000 |  | 30000 | 5100 |  | 30000
| 8 | 136 West Ferry | Wake Mod-3 | 2021-11-30 | SONYMA | 195000 | 160000 | 160000 |  | 160000 | 38400 | 8000 | 0 | 113600 |  |  | 35000 |  |  | 5100 | 11700
| 9 | 312 Busti | Wake Mod-5 | 2022-01-15 | NWB-HFHB | 185000 | 165000 | 165000 |  | 165000 |  | 8000 | 173000 |  |  |  | 35000 |  | 30000 | 5100
| 10 | 423 Busti | Wake Mod-4 | 2022-01-31 | SONYMA | 175000 | 155000 | 155000 |  | 155000 | 37200 | 8000 |  | 109800 |  |  | 35000 |  | 30000 | 5100
| 11 | 503 Busti | Wake Mod 5 | 2022-02-15 | NWB-HFHB | 185000 | 165000 | 165000 |  | 165000 |  | 8000 | 173000 |  |  |  | 35000 |  | 30000 | 5100
| 12 | 33 Brunswick | ACES 3 bdrm Nwbld | 2022-02-28 | SONYMA | 175000 | 155000 | 155000 |  | 155000 | 37200 | 8000 |  | 109800 |  |  | 35000 |  |  | 5100
| 13 | 171 Hastings | R-4 | 2022-03-31 | NWB HFHB | 155000 | 90000 | 90000 |  | 90000 |  | 8000 | 98000 |  |  | 28000 |  |  |  | 5100 | 15000
| 14 | 20 Andrews | R-3 | 2022-03-31 | NWB-HFHB | 155000 | 128000 | 128000 |  | 128000 |  | 8000 | 136000 |  |  | 28000 |  |  | 30000 | 5100
| 15 | 59 Verplanck | Floyd | 2022-03-31 | SONYMA | 175000 | 145000 | 145000 |  | 145000 | 34800 | 8000 |  | 102200 |  |  | 35000 |  |  | 5100
| 16 | 117 Center St | Floyd bld | 2022-03-31 | Partner | 175000 | 130000 | 180000 | 31200 | 148800 |  | 0 |  |  | 148800 |  |  |  |  | 5100
| 17 | 65 Verplanck | Floyd | 2022-04-15 | NWB-HFHB | 175000 | 145000 | 145000 |  | 145000 |  | 8000 | 153000 | [6 empty] | 5100
| 18 | 19 Phyllis | R-4 1.5 Bath | 2022-04-15 | NWB-HFHB | 145000 | 90000 | 90000 |  | 90000 |  | 8000 | 98000 |  |  | 28000 |  |  | 30000 | 5100 | 15000
| 19 | 114 or 116 Center St | Ranch Accesable | 2022-04-15 | Partner | 175000 | 140000 | 180000 | 33600 | 146400 |  | 0 |  |  | 146400 |  |  |  |  | 5100
| 20 | 69 Verplanck | 4 bdrm Ranch access | 2022-04-30 | NWB-HFHB | 175000 | 145000 | 145000 |  | 145000 |  | 8000 | 153000 |  |  |  | 35000 |  |  | 5100
| 21 | 204 Woodlawn | R-5 | 2022-04-30 | SONYMA | 165000 | 120000 | 120000 |  | 120000 | 28800 | 8000 |  | 83200 |  | 28000 |  | 30000 |  | 5100 |  | 30000
| 22 | 142 Wende | Ranch O BOCES 19-21 | 2022-05-15 | NWB-HFHB | 155000 | 125000 | 125000 |  | 125000 |  | 8000 | 133000 |  |  |  | 35000 |  |  | 5100
| 23 | 37 Haven | R-3 | 2022-05-15 | NWB-HFHB | 145000 | 80000 | 80000 |  | 80000 |  | 8000 | 88000 |  |  | 28000 |  |  | 30000 | 5100 |  |  | 30000
| 24 | 114 Wende | School Bld Mod 3bdrm | 2022-05-15 | NWB-HFHB | 155000 | 125000 | 125000 |  | 125000 |  | 8000 | 133000 | [6 empty] | 5100
| 25 | 162 Zenner (Youth Bld) | R-3 | 2022-06-15 | NWB-HFHB | 145000 | 80000 | 80000 |  | 80000 |  | 8000 | 88000 |  |  | 28000 |  | 30000 |  | 5100
| x | 85 Haven | [20 empty] | 30000
| x | 29 Minton | [20 empty] | 30000
| x | 147 Zenner | [20 empty] | 30000
[6 empty] | 4110000 | 3083000 |  |  | 3290200 | 246000 | 152000 | 1584000 | 723000 | 607200 | 168000 | 385000 | 60000 | 270000 | 117300 | 41700 | 120000 | 120000
[14 empty] | 1330200 |  |  |  |  | 1282000
[14 empty] | ALL CASH at TABLE |  | ALL GRANT INCOME
SALES FY22 for budget purposes only
Formulas:
c of o date FY21 = [c of o date FY21, row below]-35
Note on D24: Rick Folger: Orleans BOCES 19-21
Note on D29: Rick Folger: BOCES Potter Road pulled after 6-21. Not sure how complete this home will be
Note on D30: Rick Folger: Potter Rd BOCES 19-20. Currently Stored.
Note on D42: Rick Folger: Potter Rd BOCES 19-20. Currently Stored.
Note on D61: Rick Folger: Orleans BOCES 19-21
Note on D63: Rick Folger: BOCES Potter Road pulled after 6-21. Not sure how complete this home will be