## Story _ half House Construction
Priority | Task Name | Predecessors | Duration | Start Date | End Date | Assigned To | Status | % Done | Notes
| New House Build Schedule = 2 Story |  | 86.5d | 2021-05-11 | 2021-09-08
| Interval 1 |  | 1d | 2021-05-11 | 2021-05-11
| Project Mobilization |  | 1d | 2021-05-11 | 2021-05-11 |  | Not Started
| Architect/Engineer | 3 | 0 | 2021-05-11 | 2021-05-11
| Permits | 4 | 0 | 2021-05-11 | 2021-05-11
| Interval 2 - Site Mobilization |  | 18d | 2021-05-12 | 2021-06-04
| Site Prep | 5 | 1d | 2021-05-12 | 2021-05-12
| Porta-Potty on site | 5 | 1d | 2021-05-12 | 2021-05-12
| Dumpster on site | 5 | 1d | 2021-05-12 | 2021-05-12
| Foundation staked out | 5 | 1d | 2021-05-12 | 2021-05-12
| Excavation and Hauling | 10 | 1d | 2021-05-13 | 2021-05-13
| Footers and Foundation | 11 | 10d | 2021-05-14 | 2021-05-27
| Footers | 11 | 2d | 2021-05-14 | 2021-05-17
| Form the footers |  | 1d | 2021-05-14 | 2021-05-14
| Stone and rebar footers |  | 1d | 2021-05-14 | 2021-05-14
| footing inspection | 15 | 1d | 2021-05-17 | 2021-05-17
| concrete pour for the footers |  | 1d | 2021-05-14 | 2021-05-14
| Foundation Walls | 17 | 5.5d | 2021-05-17 | 2021-05-24 | subcontract
| form the foundation walls | 17 | 2d | 2021-05-17 | 2021-05-18
| tie in rebar for the foundation walls | 19 | 1d | 2021-05-19 | 2021-05-19
| Pour the foundation walls | 20 | 1d | 2021-05-20 | 2021-05-20
| pull foundation wall forms | 21 | 1d | 2021-05-21 | 2021-05-21
| Lay the drainage piping at footings | 21 | 0.5d | 2021-05-21 | 2021-05-21
| Apply waterproofing system to exterior foundation | 23 | 1d | 2021-05-21 | 2021-05-24
| Basement floor Flat work & sump crock/pump | 24 | 1d | 2021-05-24 | 2021-05-25
| Set Steel Girders and posts | 25 | 0.5d | 2021-05-25 | 2021-05-25
| Water & sewer from street | 26 | 1d | 2021-05-26 | 2021-05-26 | subcontractor
| Backfill & rough grade | 27 | 1d | 2021-05-27 | 2021-05-27 | subcontractor
| Framing to Deck | 28 | 6d | 2021-05-28 | 2021-06-04 | Michael
| Install PT 2x6 sill plate with sill seal | 28 | 0.5d | 2021-05-28 | 2021-05-28 | Michael
| install 2x4 beam plate | 28 | 0.1d | 2021-05-28 | 2021-05-28 | Michael
| layout plate for joists | 30 | 0.25d | 2021-05-28 | 2021-05-28 | Michael
| install floor joists (non-driveway side) | 32 | 1d | 2021-05-28 | 2021-05-31 | Michael
| install floor joists (driveway side) | 33 | 1d | 2021-05-31 | 2021-06-01 | Michael
| install bridging | 34 | 0.25d | 2021-06-01 | 2021-06-01 | Michael
| check center beam for level | 35 | 0.1d | 2021-06-02 | 2021-06-02 | Michael
| install foam board rim insulation | 34 | 0.5d | 2021-06-01 | 2021-06-02 | Michael
| install floor deck | 34 | 2d | 2021-06-01 | 2021-06-03 | Michael
| install basement stairs | 38 | 0.25d | 2021-06-03 | 2021-06-03 | Michael
| install block window and egress windows | 39 | 1d | 2021-06-04 | 2021-06-04 | subcontractor
| Interval 3 - Enclosure |  | 31d | 2021-06-03 | 2021-07-16 |  |  |  | site super comes on board
| Framing 1st Floor | 38 | 2.5d | 2021-06-03 | 2021-06-08
| Layout plates for 1st floor | 38 | 0.5d | 2021-06-03 | 2021-06-04
| cut and assemble headers for windows/doors | 39 | 0.5d | 2021-06-04 | 2021-06-04
| frame & sheath exterior walls, brace for plumb | 43 | 1d | 2021-06-04 | 2021-06-07
| frame interior 1st floor walls | 45 | 1d | 2021-06-07 | 2021-06-08
| install double plates | 43 | 0.5d | 2021-06-04 | 2021-06-04
| layout rim joists | 44 | 0.5d | 2021-06-04 | 2021-06-04
| Framing - Porch | 48 | 2.25d | 2021-06-07 | 2021-06-09
| pour concrete piers - if not done | 48 | 1d | 2021-06-07 | 2021-06-07 |  |  |  | should the mason cont do this?
| attach floor beam to concrete piers | 50 | 0.25d | 2021-06-08 | 2021-06-08
| install & flash porch ledger board at house | 50 | 0.25d | 2021-06-08 | 2021-06-08
| install porch floor joists - temp deck | 51 | 0.5d | 2021-06-08 | 2021-06-08
| install porch posts/columns | 53 | 0.5d | 2021-06-08 | 2021-06-09
| Framing 2nd Floor | 54 | 5.5d | 2021-06-09 | 2021-06-16
| install 2nd floor joists | 54 | 1d | 2021-06-09 | 2021-06-10
| install 2nd floor decking | 56 | 1d | 2021-06-10 | 2021-06-11
| Layout plates for 2nd floor walls | 57 | 0.5d | 2021-06-11 | 2021-06-11
| cut and assemble headers for windows/doors | 58 | 0.5d | 2021-06-11 | 2021-06-14
| frame & sheath exterior walls, brace for plumb | 56 | 2d | 2021-06-10 | 2021-06-14
| frame interior 2nd floor walls | 60 | 1d | 2021-06-14 | 2021-06-15
| install double plates | 61 | 0.5d | 2021-06-15 | 2021-06-15
| layout for trusses | 62 | 0.5d | 2021-06-15 | 2021-06-16
| install 1st to 2nd floor stairs | 63 | 0.5d | 2021-06-16 | 2021-06-16
| install porch roof - temp brace to house | 60 | 0.5d | 2021-06-14 | 2021-06-14
| Roofing | 64 | 13d | 2021-06-16 | 2021-07-05
| install porch ceiling joists & rafters & rakes | 64 | 1d | 2021-06-16 | 2021-06-17 | volunteers
| install porch roof fascia & sheathing | 67 | 1d | 2021-06-17 | 2021-06-18
| build rakes & attach to the gable end trusses | 68 | 1d | 2021-06-18 | 2021-06-21 | subcontractor
| raise trusses install bracing | 69 | 1d | 2021-06-21 | 2021-06-22
| install hurricane clips | 70 | 1d | 2021-06-22 | 2021-06-23
| install fascia | 71 | 1d | 2021-06-23 | 2021-06-24
| install sheathing | 72 | 1d | 2021-06-24 | 2021-06-25
| install ice & water shield | 73 | 1d | 2021-06-25 | 2021-06-28
| install roofing felt on main & porch roof | 74 | 1d | 2021-06-28 | 2021-06-29
| install drip edge on main & porch roof | 75 | 1d | 2021-06-29 | 2021-06-30
| install shingles on main & porch roof | 76 | 1d | 2021-06-30 | 2021-07-01
| wrap fascia & rakes with aluminum | 77 | 1d | 2021-07-01 | 2021-07-02 | sub 2
| install gutters | 78 | 1d | 2021-07-02 | 2021-07-05 | sub 3
| Windows and Doors | 79 | 4d | 2021-07-05 | 2021-07-09 |  |  |  | site super back on site
| Install House Wrap | 79 | 1d | 2021-07-05 | 2021-07-06
| check rough openings, flash windows & door openings | 81 | 1d | 2021-07-06 | 2021-07-07
| install windows & doors | 82 | 2d | 2021-07-07 | 2021-07-09
| Siding | 83 | 5d | 2021-07-09 | 2021-07-16
| install soffit and fascia on porch | 83 | 1d | 2021-07-09 | 2021-07-12
| install starter strip and J Blocks | 85 | 1d | 2021-07-12 | 2021-07-13
| install corner, window & door trim | 86 | 1d | 2021-07-13 | 2021-07-14
| install siding on walls | 87 | 1d | 2021-07-14 | 2021-07-15
| Porch |  | 1d | 2021-07-09 | 2021-07-12
| build porch stairs & install | 67 | 0.5d | 2021-07-09 | 2021-07-12
| install porch decking & stair treads | 67 | 1d | 2021-07-09 | 2021-07-12
| install porch railings | 68 | 0.75d | 2021-07-09 | 2021-07-12
| completely seal, caulk all penetrations | 88 | 1d | 2021-07-15 | 2021-07-16 |  |  |  | site super moves to next site
| Interval 4 - MEP | 0 | 6.75d | 2021-07-16 | 2021-07-26
| HVAC Rough | 93 | 4d | 2021-07-16 | 2021-07-22
| run supply and return ducts | 93 | 3d | 2021-07-16 | 2021-07-21
| inspection |  |  | 2021-07-16
| install furnace | 96 | 1d | 2021-07-21 | 2021-07-22
| final inspection |  |  | 2021-07-16
| Plumbing Rough | 93 | 4.5d | 2021-07-16 | 2021-07-23
| install rough to tubs | 61 | 0.25d | 2021-07-16 | 2021-07-16
| install hot and cold water runs - PEX | 93 | 2d | 2021-07-16 | 2021-07-20
| install drains and vent pipes | 102 | 2d | 2021-07-20 | 2021-07-22
| inspection - pressure test drains, waste & vents | 103 | 0.5d | 2021-07-22 | 2021-07-23
| Electrical Rough | 93 | 6d | 2021-07-16 | 2021-07-26
| install meter and service goose neck - if not done | 78 | 1d | 2021-07-16 | 2021-07-19
| inspect exterior electrical |  |  | 2021-07-16
| install backer board in basement for panel | 106 | 1d | 2021-07-19 | 2021-07-20
| install panel | 108 | 1d | 2021-07-20 | 2021-07-21
| install home run wiring, boxes | 109 | 1d | 2021-07-21 | 2021-07-22
| label all circuits in panel | 110 | 1d | 2021-07-22 | 2021-07-23
| call for rough electrical inspection | 111 | 1d | 2021-07-23 | 2021-07-26
| energize house & set up alarms |  |  | 2021-07-16
| Driveway and sidewalks | 113 |  |  |  | subcontractor
| prep for driveway & sidewalks | 113 | 0.5d
| pour concrete for sidewalks | 115 | 0.5d
| blacktop by contractor | 115 | 0.5d
| Landscaping | 117 |  |  |  | volunteers |  |  | site super is back to this site
| spread topsoil | 117 | 0.5d
| spread grass seed | 119 | 0.25d
| Insulation |  |  |  |  | volunteers
| install baffles in attic | 117 | 1d
| seal all electrical boxes - interior | 122 | 0.5d
| install cavity insulation in walls & attic | 123 | 2d
| blow in insulation in attic to correct depth | 124 | 0.5d
| install basement insulation batts |  | 1d
| insulation inspection | 125 | 1d
| Build and install shed |  | 1d | 2021-07-16 | 2021-07-16
Drywall
| load drywall | 125 | 1d
| install ceiling drywall | 130 | 2d
| install drywall on walls | 131 | 3d
| Drywall lag - clear out for finishers | 132 | 1d
| drywall finishing | 133 | 7d |  |  | subcontractor |  |  | super leaves for next site
| Interval 5 - Interior Finishes |  | 3.5d | 2021-09-03 | 2021-09-08
| Interior Paint |  | 3d | 2021-09-03 | 2021-09-07 |  |  |  | super comes back to site
| ceilings | 134 | 1d
| walls primer & top coat | 137 | 1d
| casings & doors | 138 | 1d
| Install interior doors | 139 | 1d
| paint basement stairs |  | 0.1d
| install hard surface flooring | 140 | 2d
| install luan for vinyl floring areas | #REF | 1d | 2021-09-07 | 2021-09-07
| install vinyl plank in bathrooms |  | 1d | 2021-09-03 | 2021-09-03
| Door Casings / Base | #REF | 1d | 2021-09-06 | 2021-09-06
Cabinets & Countertops
| install cabinets | 142 | 1d
| install countertops & backsplash | 147 | 1d | [5 empty] | site super leaves for next site
Electrical Final
| install lights and box covers | 148 | 1d
| install stove hood | 148 | 1d
| Plumbing Final | 148
| cut countertop for kitchen sink & install it & bath sinks | 148 | 1d
| install faucets and connect drains | 153 | 1d
install hot water tank
| HVAC Final | 148
| install all vent covers | 139 | 0.5d
| install furnace furnace & filter | 139 | 0.25d
| install thermostat | 139 | 0.25d
| Interior Trim & Flooring | #REF | 2d | 2021-09-03 | 2021-09-06
| install door knobs & stops | #REF | 1d | 2021-09-03 | 2021-09-03
| install bathroom & closet & cabinet hardware | #REF | 1d | 2021-09-06 | 2021-09-06
| Install Appliances | #REF | 0.5d | 2021-09-07 | 2021-09-07
Call for final MEP inspections
| Flooring | 159
| install carpet | 159 | 1d |  |  | subcontrator
| Interior Punchlist | 163 | 1d | 2021-09-07 | 2021-09-08
Interval 6 - Exterior Finishes
| Exterior Punchlist | 120 | 1d
| Interval 7 - Consumables Allowance | 169 | 1d
Blower door test

## Sheet1
Floyd House Build 1-1/2 Story
Task Name
Interval 1
| Project Mobilization | Done months in advance, manged by Construction Field Manager with support from Construction Coordinator
Architect/Engineer
Permits
Interval 2 - Site Mobilization
| Site Prep | Contracted out through Constructuion Field Manager with support from Construction Coordinator
Porta-Potty on site
Dumpster on site
Foundation staked out
Excavation and Hauling
Footers and Foundation
Footers
Form the footers
Stone and rebar footers
footing inspection
concrete pour for the footers
Foundation Walls
form the foundation walls
tie in rebar for the foundation walls
Pour the foundation walls
pull foundation wall forms
Lay the drainage piping at footings
Apply waterproofing system to exterior foundation
Basement floor Flat work & sump crock/pump
Set Steel Girders and posts
Water & sewer from street
Fabric and Stone drainage piping at footings
Backfill & rough grade
Auger porch foundation piers
Place concrete for foundation piers
| Framing to Deck | Alternative Building Site Super using Home Team only Build Days
Install PT 2x6 sill plate with sill seal
install 2x4 beam plate
layout plate for joists
install floor joists
install floor joists (driveway side)
install bridging
check center beam for level
install foam board rim insulation
install floor deck
install basement stairs
install temporary security blocking for egress windows
| install block window | Site Super oversees subcontractor
Interval 3 - Enclosure
| Framing 1st Floor | Traditional Site Super w Volunteers (has two weeks to complete) | Time Period A
Layout plates for 1st floor
cut and assemble headers for windows/doors
frame & sheath exterior walls, brace for plumb
frame interior 1st floor walls
install double plates
Framing - Porch
pour concrete piers - if not done
attach floor beam to concrete piers
install & flash porch ledger board at house
install porch floor joists - temp deck
install porch posts/columns
| Roofing | Traditional Site Super oversees subcontractor who was contracted by Construction Field Manager (has two weeks to complete) | Time Period B
raise trusses install bracing
install roof sheathing
install ice & water shield
install drip edge
install shingles on main
install facia and rakes
wrap facia and rakes
| Framing 2nd Floor - Exterior Finish | Traditional Site Super w Volunteers (has three weeks to complete) | Time Period C
install 1st to 2nd floor stairs
install 2nd floor decking
Layout plates for 2nd floor interior walls
cut and assemble headers for windows/doors
frame interior 2nd floor walls
install double plates
install porch roof - temp brace to house
install porch ceiling joists & rafters & rakes
install porch roof fascia & sheathing
install ice & water shield
install roofing felt porch roof
install drip edge on porch roof
install shingles on porch roof
wrap fascia & rakes with aluminum
Windows and Doors
Install House Wrap
check rough openings, flash windows & door openings
install windows & doors
Siding
install soffit and fascia on porch
install starter strip and J Blocks
install corner, window & door trim
install siding on walls
Porch
build porch stairs & install
install porch decking & stair treads
install porch railings
completely seal, caulk all penetrations
Interval 4 - MEP
| HVAC Rough | Traditional Site Super oversees specialty crews and subcontractors who were contracted by Construction Field Manager (has three weeks to complete) | Time Period D
run supply and return ducts
inspection
install furnace
final inspection
Plumbing Rough
install rough to tubs
install hot and cold water runs - PEX
install drains and vent pipes
inspection - pressure test drains, waste & vents
Electrical Rough
install meter and service goose neck - if not done
inspect exterior electrical
install backer board in basement for panel
install panel
install home run wiring, boxes
label all circuits in panel
call for rough electrical inspection
energize house & set up alarms
Install Gutters
Driveway and sidewalks
prep for driveway & sidewalks
pour curbs and aprons
pour concrete for sidewalks
blacktop by contractor
| Landscaping | AmeriCorps led with Volunteers (one week to complete) | Time Period E
spread topsoil
spread grass seed
Interval 5 - Interior Finishes
| Insulation | Traditional Site Super w Volunteers (has two weeks to complete) | Time Period F
install baffles in attic
seal all electrical boxes - interior
install cavity insulation in walls & attic
blow in insulation in attic to correct depth
install basement insulation batts
insulation inspection
Build and install shed
Drywall
load drywall
install ceiling drywall
install drywall on walls
Drywall lag - clear out for finishers
| Drywall Finishing | Traditional Site Super oversees subcontractor | Time Period G
| Interior Paint | Traditional Site Super w Volunteers (has five weeks to complete) | Time Period H
ceilings
walls primer & top coat
casings & doors
Install interior doors
paint basement stairs
install hard surface flooring
install luan for vinyl floring areas
install vinyl plank in bathrooms
Door Casings / Base
Cabinets & Countertops
install cabinets
install countertops & backsplash
Electrical Final
install lights and box covers
install stove hood
Plumbing Final
cut countertop for kitchen sink & install it & bath sinks
install faucets and connect drains
install hot water tank
HVAC Final
install all vent covers
install furnace furnace & filter
install thermostat
Interior Trim & Flooring
install door knobs & stops
install bathroom & closet & cabinet hardware
Install Appliances
Call for final MEP inspections
| Carpet |  | Time Period I
Blower door test
Interior Punchlist
Exterior Punchlist